## Schedule
Guidance: this tool is to be used as a guideline to help you plan your activities for the trachoma surveys. Not all stages may be applicable. Please note that we recommend you allocate specific activites to different accountable owners. These may be individuals within the MoH, Co-ordinating or Implementing Agencies. You may find that some activities are highly dependent on multiple stakeholders. We recommend you name the accountable owner and identify who has shared responsibility. Perhaps use RACI (Responsible, Accountable, Consulted, Informed).
Project planning tool for Coordinating/Implementing Agencies to work in conjunction with the MoH
| w/c dd/mm/yyyy | w/c | w/c | w/c | w/c | w/c
Governance
Establish national steering committee or national trachoma task force
Identify national Epidemiologist to join steering committee (if large country)
National steering committee or task force to engage with MOH (NTDs and all relevant departments) and WHO office, as necessary
Establish sub-national steering committees, as necessary
Identify (implementing) partners to conduct surveys (through national steering committee or task force)
Agree overall governance structure
Governmental and NGO partners agree to terms of work on Tropical Data website
Districts/evaluation units to be surveyed
Identify districts/evaluation units to be surveyed
Obtain available census data and supply to Tropical Data epidemiologist & Data Manager at ITI
Agree sampling methodology and clusters to be mapped
Consents
Apply for ethics review and approval at the national level (and sub-national level, as required)
Determine if any materials need to be obtained outside of the country and request exemption from import duties
Establish guidelines for obtaining consent from village leaders and survey participants
Data collection and management
Determine capacity for use of Androids (network coverage etc)
Determine strategies to share survey findings nationally and internationally
Agree MOU at national level to use electronic data transfer and confimation of willingness to share data
Agree process for data management (approvals, analysis, reporting)
Identify individuals in MOH who will approve data and put them in contact with Tropical Data, Data Manager at ITI
Procure and set-up Androids
Develop plan
Agree organisational structure
Establish work schedule and timelines
Develop and agree (with MoH and grant manager) budget and plan - including per diems, transport costs, training and sensitisation activities
Training (see Tropical Data training manual)
Once dates established, work with a Tropical Data epidemiologist to identify potential grader and recorder trainers
Identify potential graders and recorders
Establish training date and identify training sites
Identify and deliver equipment required for training and mapping (including time needed for shipping)
Hold a grader and recorder training workshop (classroom and field)
Mapping
Check all resources in place - teams, vehicles, Androids, etc (see Tropical Data training manual)
Sensitise residents of first clusters to be included
Launch surveys
Version_01