## Challenge Project Plan
| Quick Tips | Status | Date | Owner | Completed
Defining Challenge Outcomes
Key Milestone: challenge Launch Date
Key Milestone: challenge End Date
Challenge Sponsor Interview | Align with the sponsor on the following items: |  |  |  |  | Outside of Innovation Central
Define objectives | Define the business outcome(s) to be achieved |  |  |  |  | Outside of Innovation Central
Roles & Resources | Explain the roles of a challenge & gain recommendations from sponsor for review, audience & understanding of who will execute ideas |  |  |  |  | Outside of Innovation Central
Timeline Expectations | Work with the sponsor to define launch date, duration of challenge & when final decisions are to be made |  |  |  |  | Outside of Innovation Central
Align on Plan | Once you've finalized the plan, email or discuss with challenge sponsor |  |  |  |  | Outside of Innovation Central
Ideate & Collaborate
Key Milestone: Content Completion Date
Key Milestone: Content Finalized into Idea Central Date
Introduction | Craft an introduction that is clear, attention grabbing & inspiring |  |  |  |  | Configure within Innovation Central
Idea Form | Align the idea form with the review criteria & introduction. Help people think through the idea using the flow of the form. |  |  |  |  | Configure within Innovation Central
Seed Ideas | 3-5 seed ideas - Seed Ideas model what is expected, and overcomes "going first" |  |  |  |  | Configure within Innovation Central
Engagement | What special considerations exist for driving engagement from intended audience? |  |  |  |  | Configure within Innovation Central
Engage & Inspire
Key Milestone: Pre-challenge Communications Date
Key Milestone: Launch Email Date
Key Milestone: Reminder Email Date
Key Milesonte: Final Call Email Date
Event Access | Configure the individuals who will have access to the challenge |  |  |  |  | Configure within Innovation Central
Internal Communication & Marketing | If this is the first exposure to a challenge, consider communications for awareness. This might be posters, attending staff meetings, answering questions in the breakroom, etc. |  |  |  |  | Outside of Innovation Central
Audience Email | Series of launch, reminder, closure emails telling your participants when & how to participate |  |  |  |  | Configure within Innovation Central
Contributor Communication | Thank you notes to those who input ideas |  |  |  |  | Configure within Innovation Central
Define Help Approach | Who in your organization will be the point of contact to help with technical or challenge questions? |  |  |  |  | Configure & Outside of Innovation Central
Recognition | Consider the behaviors you want to recognize (ie participation & collaboration) Emphasize recognition v. reward |  |  |  |  | Outside of Innovation Central
Post challenge Commuication | Sharing the stories, outcomes and lessons learned with the organization is vital for long-term success. |  |  |  |  | Configure & Outside of Innovation Central
Day-to-Day Management | Who will be monitoring results, making tactical changes / decisions as needed? |  |  |  |  | Outside of Innovation Central
Review & Decide
Key Milestone: Review Team Training Date
Key Milestone: Review Process Start Date
Key Milestone: Review Process End Date
Define Review Criteria | Define criteria for choosing top concepts. Ensure the criteria are clear and unambiguous |  |  |  |  | Configure within Innovation Central
Review Team Training for Catalyst Activities | What are the steps to define, configure and train reviewers? What type of criteria will be used? |  |  |  |  | Outside of Innovation Central
Review Team Training for Decision Making Activities | Need to know the steps to complete a mass review, full review, etc. depending on what method you are using |  |  |  |  | Outside of Innovation Central
Schedule Review process timeline / training on calendars | Ensure the Review members know what to do, when by putting calendar invites / reminders |  |  |  |  | Outside of Innovation Central
Conclude, Report & Close
Key Milestone: Conclusions Completed
Key Milestone: Analysis and Reports Completed
Key Milestone: Challenge Archived
Conclusions | Use the conclusion functionality to ensure idea generators receive follow-through – may also consider a mass email from Campaign Management or Contributor Communication to let everyone know global outcomes
Analysis of results, outcomes and lessons learned | What is important to share with a wider audience, how can we use this opportunity for culture change and story telling?
Archive the challenge | Finalize and archive the challenge to preserve the ideas and prepare for the next challenge