## Weekly
HBA Event Planning Checklist
This checklist will walk you step-by-step through the planning process from start to finish. Event planning is a detailed and intricate process so this checklist might look overwhelming at first. Please use the list in bite-sized pieces based upon where you are in the process to make the list more manageable for your team.
Please enter your event date (or target event date) where indicated in red, as well as event planning team members name to take advantage of the full functionality of this checklist
Event details: |  |  | Event Planning Team | Name
Event Date: | [event date] |  | Event Logistics: | [insert name]
Event Title: |  |  | Content | [insert name]
Location/sponsor: |  |  | Sponsor/venue: | [insert name]
|  |  | Marketing liaison: | [insert name]
|  |  | Membership and Volunteer liaison: | [insert name]
X | Planning Item | Due date and action owner | Status / Comments / Followups | Notes / next steps | Resources/tools
X | Set up weekly Event Planning meeting w/ full team | [insert name]
By Week 12 |  | #VALUE!
Sponsor workstream
| Confirm potential event date(s) with venue/sponsor | [insert name] |  | Confer with Content volunteer and Programming DAL to ensure date works for all parties. Please try to avoid major holidays
| Secure from venue/sponsor: | [insert name] |  | Input all final details onto Event Setup Form | HBA Event Setup Form
• Directions to location
• Capacity of event room
• Reservation or room rental (if needed)
| • Any special instructions |  |  | i.e. arrival, parking or security info needed for attendees
| Sponsored events: secure preferred company logo and website | [insert name]
| Share HBA In-Kind Form and donor letter with sponsor company with instruction that they complete soon after event | [insert name] |  |  | HBA In-Kind Receipt Form HBA Donor Letter
Speaker workstream
| Interview/determine potential event speaker(s) | [insert name]
| Confirm potential event date(s) with speaker(s) | [insert name] |  | Confer with Sponsor/venue volunteer and Event DAL before solidifying date
| Confirm speaker(s) participation and session specifics | [insert name]
| Select appropriate Leadership Competencies | [insert name] |  |  | HBA Leadership Competency Framework
| Develop session Learning Objectives | [insert name] |  |  | Action Verbs for developing learning objectives - hyperlinked into the Event Setup Form
| Prepare event content details and agenda | [insert name] |  | Draft event title, short description, event details, program flow
| Secure from speaker(s): | [insert name]
• Biography
• Photo
• Email address
• Twitter handle
| • Signed HBA Speaker Agreement |  |  |  | HBA Speaker Agreement
| Input all speaker and content details into Event Setup Form and share with Marketing volunteer | [insert name]
Week 10 |  | #VALUE!
Marketing and Finance Workstream - 8-9 weeks out |  | #VALUE!
| Review and confirm the following with your chapter vice president: | [insert name] |  | VP will discuss any needs with regional treasurer and committees
• Event budget
• Event revenue targets
| • Event pricing (member/nonmember) |  |  |  | HBA Programming Policies
• Payment method and/or invoicing
• Necessary discount codes
| • Any contracts that may need to be signed |  |  | Regional Treasurer is the only volunteer authorized to sign contracts and legal documents
| Marketing reviews and adds "sizzle to event title, short description and event details, then returns to Event Logistics volunteer | [insert name]
Week 9 |  | #VALUE!
| Determine onsite volunteer staffing needs | [insert name] |  | Refer to Onsite Team Roles tab of this workbook to assist in determining needs. | Event Volunteer Staffing Grid
| Develop event marketing strategy | [insert name] |  | Determine frequecy of social media/other promotion. Use of Digital Elite, etc.
| Compile all final event information onto HBA Event Setup Form | [insert name]
Week 8 |  | #VALUE!
| Submit Event Setup Form to HBA Central | [insert name] |  | Submit to events@hbanet.org along with any other files that need to be linked onto the registration page
| Event registration page set up online | HBA Central |  | By Bridget Fairbanks, events@hbanet.org
| List event on chapter homepage w/ graphic slider | HBA Central |  | By Bridget Fairbanks, events@hbanet.org
| Event will be automatically included in weekly Event Digest emails | HBA Central |  | By Stephanie Marchak, smarchak@hbanet.org.
| Event speaker(s) registered online | HBA Central |  | By Bridget Fairbanks, events@hbanet.org
| Event feedback surveys created and set to go out immediately post-event | HBA Central |  | Created by Lori Whitehand, lwhitehand@hbanet.org
| Completed Event Form returned to team w/ registration link and all discount codes | HBA Central |  | By Bridget Fairbanks, events@hbanet.org
Week 7 |  | #VALUE!
| Create marketing materials in Lucid Press and provide to planning team | [insert name] |  | By Stephanie Marchak, smarchak@hbanet.org. Includes PPT opening slide, image for social media use, marketing flyer
| Implement marketing/advertising plan | [insert name] |  | Social media, newsletter, Board promotion, other. Use social media image and marketing flyer provided by HBA Central
| Create event marketing materials in LucidPress | [insert name]
| Begin monitoring event attendance | [insert name] |  | Event DAL has access to real-time event attendance reports and should either provide to team regularly to monitor or contact Katie Cammer, kcammer@hbanet.org, to request direct access for Event Logistics volunteer. If attendance is low, consider revising marketing plan | How to access Event Attendance Reports
Week 6 |  | #VALUE!
Venue/sponsor internal planning
| Venue floor plan / layout: | [insert name]
| Speaker/presentation area |  |  | Raised stage preferred if available, discuss chair/table set up needs for speaker(s), water bottles available. Podium/mic available for opening/closing remarks?
| Audience set-up |  |  | Set up theater style, cresent rounds, etc. Ensure all attendees face partially forward - no backs to the presentation area
| Overall room setup |  |  | Discuss where networking area will be with collateral table, food/bev setup, etc
Expected event flow/traffic
| Logistics: | [insert name]
| Registration area (tables, chairs, easels) |  |  | 1-2 6ft tables for registration, 2-3 chairs, table cloth, # easles for signage, trash can, coat rack (if needed)
| Collateral area |  |  | 1-2 tables near networking area for HBA membership/volunteer info, affinity group info, etc
| New Member orientation breakout group |  |  | if applicable. When/where during program?
| Food / refreshments | [insert name] |  | Like to offer a 'lite dinner'; offer a few vegetarian/gluten free options; Cash bars at Dine Arounds.
| Audio/Visual | [insert name]
| Micophones |  |  | For speaker(s) and Q&A - lavalier mics pref for speaker(s), 1-2 hand-helds for Q&A
| Screen/projector/sound needs |  |  | Confirm what is available vs. what is needed
| Presentation shown via ____? |  |  | Venue AV or need committee member laptop for presentation?
AV tech available pre-event/during event?
Week 5 |  | #VALUE!
| Sponsored event: confirm Sponsor "Host" for welcome remarks | [insert name]
| Review all logistics items provided by sponsor/venue liaison and follow up if necessary | [insert name] |  | Confirm all internal logistical planning details are sufficient for the event
Week 4 |  | #VALUE!
| Finalize program flow / format | [insert name]
| Develop v1 of the slide presentation for event | [insert name] |  | When complete, send to event logistics volunteer | HBA PowerPoint Template
| Finalize speaker materials to be used onsite (slides, handouts, biographies) | [insert name] |  | Final versions due to event logistics volunteer 10 days prior to event
| Confirm AV needs of speaker (if any) | [insert name] |  | Share with venue/sponsor liaison
| Arrange and conduct practice session of program virtually via teleconference or webinar platform | [insert name]
Week 3 |  | #VALUE!
| Identify HBA 'host' for the event | [insert name] |  | HBA Host: chapter EC/board/committee member(s) to handle HBA welcome and/or closing remarks
| Identify Volunteer to honor at event | [insert name] |  | Get volunteer headshot, quotes, bio and share with event logistics volunteer to create event slide and marketing volunteer for newsletter inclusion
| Create certificate honoring Volunteer | [insert name]
| Assign all Onsite volunteer roles and disseminate discount codes for registration | [insert name]
| Complete Event Volunteer Staffing Grid | [insert name] |  | Share with event logistics volunteer
| Brief Board on program objectives, venue, speaker | Programming DAL
| Prepare 'networking' activity (if applicable) | [insert name] |  | Design / decide on activity and provide the materials. Examples include 'Meet Me Bingo'; find your sticker-mate. Align game to meeting topic or theme if possible.
Week 2 |  | #VALUE!
| Finalize event slide deck including content slides | [insert name] |  | Using draft from content volunteer to begin
| Agenda slide |  |  | Include HBA Host name/title and event agenda
| Opening slides |  |  | About the HBA and the chapter
| Join/Volunteer slide |  |  | Membership and volunteer info
| Upcoming events |  |  | Upcoming chapter/flagship/webinar event list
| Sponsor welcome |  |  | Sponsor host name, title
| Event info |  |  | Event title, speaker name(s)
| Closing/Thank You slides |  |  | HBA closer name(s) and Thank Yous to sponsor and team
| Prepare printed event program | [insert name] |  |  | HBA Printed Program Template
| Confirm/finalize other event materials needs | [insert name] |  | Speaker gift(s), registration needs, marketing collateral materials, etc.
| Arrange for signage | [insert name]
Week 1 |  | #VALUE!
| Confirm estimated final headcount; alert venue / caterer | [insert name]
| Confirm venue's AV support and contact info | [insert name]
| Confirm all working volunteers and arrival times | [insert name]
| Review and finalize slides with HBA Host | [insert name]
| Complete all event materials preparation (see Materials List tab of this workbook) | [insert name] |  |  | Event Materials Development List
| Print event badges | [insert name] |  | Files will be available on www.hbanet.org profile for printing | How to Create Event Badges
| Conduct full virtual walkthrough session with HBA Host, Sponsor Host, speaker(s) | [insert name] |  | Make sure all titles are correct, slides in order. Confirm arrival time/location. Any specific instructions, emergency contact information or technical details.
Day of Event |  | [event date]
Logistics
| Arrive early and support/monitor caterer, AV, logistics set up as needed | [insert name] |  | monitor room set up. test mics, slide advancing, etc
| Display indoor/outdoor signage | Onsite Volunteers
| Setup and staff registration table | Onsite Volunteers |  | online registration only even for walkins | Registraion Onsite Responsibilities
| Set up collateral table set up and materials distribution | Onsite Volunteers |  |  | Engagement Onsite Responsibilities
| Support New Member Orientation (if needed) | [insert name]
| Manage volunteer staff throughout event | [insert name]
| Take photos, tweet and distribute & manage networking activity | [insert name] |  |  | Marketing Onsite Responsibilities
| Capture photos and social media coverage | [insert name]
| Manage event flow, presentation start time, etc | [insert name]
Speakers:
| Watch for and welcome speaker(s), etc | [insert name]
| Watch for and welcome sponsor and HBA hosts | [insert name]
| Hold practice/walk-through of program with HBA host, sponsor host, speaker(s) in room w/ AV | [insert name] |  | Ensure all participants are comfortable with flow, introduced to Content Timer volunteer (if needed), know who they are passing off to and when
| Oversees brief onsite program walkthrough | [insert name]
| Capture posed photos of program participants during walk through | [insert name]
Event close:
| Distribute Speaker Gift and public thank yous | HBA Host
| Close down and pack up HBA table/materials | Onsite Volunteers
| Collect all signage and pack for storage | Onsite Volunteers
Post-event
Administration |  | #VALUE!
| Personal thank you note to speaker(s) | [insert name]
| Personal thank you note to sponsor/venue contacts | [insert name]
| Summarize feedback surveys | Market Research
| Ensure completion of HBA In-Kind form by sponsor | [insert name] |  | Send complete In-Kind form to HBA Finance Department as indicated on form
Marketing |  | #VALUE!
| Review and select photos for marketing efforts/post event materials | [insert name]
| Archive event photos, etc | [insert name]
Programs |  | #VALUE!
| Conduct debriefing/lessons learned with full team | [insert name] |  | What was done well? What could have been done better for next time? What feedback was given at the event? Any highlights? Focus on both the event itself as well as the full event planning process