## Unsponsored Networking Event
HBA Event Planning Checklist
This checklist will walk you step-by-step through the planning process from start to finish. Event planning is a detailed and intricate process so this checklist might look overwhelming at first. Please use the list in bite-sized pieces based upon where you are in the process to make the list more manageable for your team.
Please enter your event date (or target event date) where indicated in red, as well as event planning team members name to take advantage of the full functionality of this checklist
Event details: |  |  | Event Planning Team | Name
Event Date: | [event date] |  | Event Logistics: | [insert name]
Event Title: |  |  | Content | [insert name]
Location/sponsor: |  |  | Sponsor/venue: | [insert name]
|  |  | Marketing liaison: | [insert name]
|  |  | Membership and Volunteer liaison: | [insert name]
X | Planning Item | Due date and action owner | Status / Comments / Followups | Notes / next steps | Resources/tools
X | Set up weekly Event Planning meeting w/ full team | [insert name]
By Week 12 |  | #VALUE!
| Confirm potential event date(s) | [insert name] |  | Confer with Programming DAL to ensure date works for all parties. Please try to avoid major holidays
| Determine event venue and secure the following details: | [insert name] |  | Aim for free or moderately priced venues with a professional/quiet atmosphere. Input all final details onto Event Setup Form | HBA Event Setup Form - Networking
• Address / directions to location
• Capacity of event room or space
• Reservation or room rental (if needed)
| • Any special instructions |  |  | i.e. arrival, parking or security info needed for attendees
Week 10 |  | #VALUE!
Marketing and Finance Workstream - 8-9 weeks out |  | #VALUE!
| Review and confirm the following with your chapter vice president: | [insert name] |  | VP will discuss any needs with regional treasurer and committees
• Event budget
• Event revenue targets
| • Event pricing (members only) |  |  |  | HBA Core Programming Guidance
• Payment method and/or invoicing
• Necessary discount codes
| • Any contracts that may need to be signed |  |  | Regional Treasurer is the only volunteer authorized to sign contracts and legal documents
| Marketing reviews and adds "sizzle to event title, short description and event details, then returns to Event Logistics volunteer | [insert name]
Week 9 |  | #VALUE!
| Determine onsite volunteer staffing needs | [insert name] |  | Refer to Onsite Team Roles tab of this workbook to assist in determining needs. | Event Volunteer Staffing Grid
| Develop event marketing strategy | [insert name] |  | Determine frequecy of social media/other promotion. Use of Digital Elite, etc.
| Compile all final event information onto HBA Event Setup Form | [insert name]
Week 8 |  | #VALUE!
| Submit Event Setup Form to HBA Central | [insert name] |  | Submit to events@hbanet.org along with any other files that need to be linked onto the registration page
| Event registration page set up online | HBA Central |  | By Bridget Fairbanks, events@hbanet.org
| List event on chapter homepage w/ graphic slider | HBA Central |  | By Bridget Fairbanks, events@hbanet.org
| Event will be automatically included in weekly Event Digest emails | HBA Central |  | By Stephanie Marchak, smarchak@hbanet.org.
| Event feedback surveys created and set to go out immediately post-event | HBA Central |  | Created by Lori Whitehand, lwhitehand@hbanet.org
| Completed Event Form returned to team w/ registration link and all discount codes | HBA Central |  | By Bridget Fairbanks, events@hbanet.org
Week 7 |  | #VALUE!
| Create marketing materials in Lucid Press and provide to planning team | [insert name]
| Implement marketing/advertising plan | [insert name] |  | Social media, newsletter, Board promotion, other. Use social media image and marketing flyer provided by HBA Central
| Begin monitoring event attendance | [insert name] |  | Programming DAL has access to real-time event attendance reports and should either provide to team regularly to monitor or contact Katie Cammer, kcammer@hbanet.org, to request direct access for Event Logistics volunteer. If attendance is low, consider revising marketing plan | How to access Event Attendance Reports
Week 6 |  | #VALUE!
| Venue floor plan / layout: | [insert name]
| Overall room setup |  |  | Discuss where networking area will be with collateral table, food/bev setup, etc
Expected event flow/traffic
| Registration area (tables, chairs, easels) |  |  | 1 table for registration, chairs, table cloth (if availalble), trash can, coat rack (if needed)
| Collateral area |  |  | Table near networking area for HBA membership/volunteer info, affinity group info, etc
| Food / refreshments |  |  | Like to offer a 'lite dinner'; offer a few vegetarian/gluten free options; Cash bars often preferred for networking events.
Week 5 |  | #VALUE!
| Review all logistics items provided by sponsor/venue liaison and follow up if necessary | [insert name] |  | Confirm all internal logistical planning details are sufficient for the event
Week 4 |  | #VALUE!
| Identify HBA 'host' for the event | [insert name] |  | HBA Host: chapter EC/board/committee member(s) to handle HBA welcome and/or closing remarks
| Assign all Onsite volunteer roles and disseminate discount codes for registration | [insert name]
| Complete Event Volunteer Staffing Grid | [insert name] |  | Share with event logistics volunteer
Week 3 |  | #VALUE!
| Brief Board on program objectives, venue, speaker | Programming DAL
| Prepare 'networking' activity (if applicable) | [insert name] |  | Design / decide on activity and provide the materials. Examples include 'Meet Me Bingo'; find your sticker-mate. Align game to meeting topic or theme if possible.
Week 2 |  | #VALUE!
| Confirm/finalize event materials needs | [insert name] |  | Speaker gift(s), registration needs, marketing collateral materials, etc. | Event Materials List
| Arrange for signage | [insert name]
Week 1 |  | #VALUE!
| Confirm estimated final headcount; alert venue / caterer and adjust reservation if needed | [insert name]
| Confirm all working volunteers and arrival times | [insert name]
| Complete all event materials preparation | [insert name] |  |  | Event Materials List
| Print event badges | [insert name] |  | Files will be available on www.hbanet.org profile for printing | How to Create Event Badges
Day of Event |  | [event date]
Logistics
| Arrive early for setup | [insert name]
| Display indoor/outdoor signageif needed | Onsite Volunteers
| Setup and staff registration table | Onsite Volunteers |  |  | Registraion Onsite Responsibilities
| Set up collateral table set up | Onsite Volunteers |  |  | Engagement Onsite Responsibilities
| Manage volunteer staff throughout event | [insert name]
| Take photos, tweet and distribute & manage networking activity | [insert name] |  |  | Marketing Onsite Responsibilities
Event close:
| Close down and pack up HBA table/materials | Onsite Volunteers
| Collect all signage and pack for storage | Onsite Volunteers
Post-event
Administration |  | #VALUE!
| Complete Event Reconciliation packet and send to HBA Central | [insert name] |  |  | Post-Event Reconciliation Instructions
| Summarize feedback surveys | Market Research
Marketing |  | #VALUE!
| Review and select photos for marketing efforts/post event materials | [insert name]
| Archive event photos, etc | [insert name]
Programs |  | #VALUE!
| Conduct debriefing/lessons learned with full team | [insert name] |  | What was done well? What could have been done better for next time? What feedback was given at the event? Any highlights? Focus on both the event itself as well as the full event planning process
| Share any important learnings with Regional Programming COE | [insert name] |  | They will incorporate into regional best practices and learnings

## Sponsored Networking Event
HBA Event Planning Checklist
This checklist will walk you step-by-step through the planning process from start to finish. Event planning is a detailed and intricate process so this checklist might look overwhelming at first. Please use the list in bite-sized pieces based upon where you are in the process to make the list more manageable for your team.
Please enter your event date (or target event date) where indicated in red, as well as event planning team members name to take advantage of the full functionality of this checklist
Event details: |  |  | Event Planning Team | Name
Event Date: | [event date] |  | Event Logistics: | [insert name]
Event Title: |  |  | Content | [insert name]
Location/sponsor: |  |  | Sponsor/venue: | [insert name]
|  |  | Marketing liaison: | [insert name]
|  |  | Membership and Volunteer liaison: | [insert name]
X | Planning Item | Due date and action owner | Status / Comments / Followups | Notes / next steps | Resources/tools
X | Set up weekly Event Planning meeting w/ full team | [insert name]
By Week 12 |  | #VALUE!
| Confirm potential event date(s) with venue/sponsor | [insert name] |  | Confer with Programming DAL to ensure date works for all parties. Please try to avoid major holidays
| Secure from venue/sponsor: | [insert name] |  | Input all final details onto Event Setup Form | HBA Event Setup Form - Networking
• Directions to location
• Capacity of event room
• Reservation or room rental (if needed)
| • Any special instructions |  |  | i.e. arrival, parking or security info needed for attendees
| Secure preferred company logo and website | [insert name]
| Share HBA In-Kind Form and donor letter with sponsor company with instruction that they complete soon after event | [insert name] |  |  | HBA In-Kind Receipt Form HBA Donor Letter
Week 10 |  | #VALUE!
Marketing and Finance Workstream - 8-9 weeks out |  | #VALUE!
| Review and confirm the following with your chapter vice president: | [insert name] |  | VP will discuss any needs with regional treasurer and committees
• Event budget
• Event revenue targets
| • Event pricing (members only) |  |  |  | HBA Core Programming Guidance
• Payment method and/or invoicing
• Necessary discount codes
| • Any contracts that may need to be signed |  |  | Regional Treasurer is the only volunteer authorized to sign contracts and legal documents
| Marketing reviews and adds "sizzle to event title, short description and event details, then returns to Event Logistics volunteer | [insert name]
Week 9 |  | #VALUE!
| Determine onsite volunteer staffing needs | [insert name] |  | Refer to Onsite Team Roles tab of this workbook to assist in determining needs. | Event Volunteer Staffing Grid
| Develop event marketing strategy | [insert name] |  | Determine frequecy of social media/other promotion. Use of Digital Elite, etc.
| Compile all final event information onto HBA Event Setup Form | [insert name]
Week 8 |  | #VALUE!
| Submit Event Setup Form to HBA Central | [insert name] |  | Submit to events@hbanet.org along with any other files that need to be linked onto the registration page
| Event registration page set up online | HBA Central |  | By Bridget Fairbanks, events@hbanet.org
| List event on chapter homepage w/ graphic slider | HBA Central |  | By Bridget Fairbanks, events@hbanet.org
| Event will be automatically included in weekly Event Digest emails | HBA Central |  | By Stephanie Marchak, smarchak@hbanet.org.
| Event feedback surveys created and set to go out immediately post-event | HBA Central |  | Created by Lori Whitehand, lwhitehand@hbanet.org
| Completed Event Form returned to team w/ registration link and all discount codes | HBA Central |  | By Bridget Fairbanks, events@hbanet.org
Week 7 |  | #VALUE!
| Create marketing materials in Lucid Press and provide to planning team | [insert name]
| Implement marketing/advertising plan | [insert name] |  | Social media, newsletter, Board promotion, other. Use social media image and marketing flyer provided by HBA Central
| Begin monitoring event attendance | [insert name] |  | Programming DAL has access to real-time event attendance reports and should either provide to team regularly to monitor or contact Katie Cammer, kcammer@hbanet.org, to request direct access for Event Logistics volunteer. If attendance is low, consider revising marketing plan | How to access Event Attendance Reports
Week 6 |  | #VALUE!
Venue/sponsor internal planning
| Venue floor plan / layout: | [insert name]
| Overall room setup |  |  | Discuss where networking area will be with collateral table, food/bev setup, etc
Expected event flow/traffic
| Registration area (tables, chairs, easels) |  |  | 1 table for registration, chairs, table cloth (if availalble), trash can, coat rack (if needed)
| Collateral area |  |  | Table near networking area for HBA membership/volunteer info, affinity group info, etc
| Food / refreshments |  |  | Like to offer a 'lite dinner'; offer a few vegetarian/gluten free options; Cash bars often preferred for networking events.
Week 5 |  | #VALUE!
| Sponsored event: confirm Sponsor "Host" for welcome remarks | [insert name]
| Review all logistics items provided by sponsor/venue liaison and follow up if necessary | [insert name] |  | Confirm all internal logistical planning details are sufficient for the event
Week 4 |  | #VALUE!
| Identify HBA 'host' for the event | [insert name] |  | HBA Host: chapter EC/board/committee member(s) to handle HBA welcome and/or closing remarks
| Assign all Onsite volunteer roles and disseminate discount codes for registration | [insert name]
| Complete Event Volunteer Staffing Grid | [insert name] |  | Share with event logistics volunteer
Week 3 |  | #VALUE!
| Brief Board on program objectives, venue, speaker | Programming DAL
| Prepare 'networking' activity (if applicable) | [insert name] |  | Design / decide on activity and provide the materials. Examples include 'Meet Me Bingo'; find your sticker-mate. Align game to meeting topic or theme if possible.
Week 2 |  | #VALUE!
| Confirm/finalize event materials needs | [insert name] |  | Speaker gift(s), registration needs, marketing collateral materials, etc. | Event Materials List
| Arrange for signage | [insert name]
Week 1 |  | #VALUE!
| Confirm estimated final headcount; alert venue / caterer and adjust reservation if needed | [insert name]
| Confirm all working volunteers and arrival times | [insert name]
| Complete all event materials preparation | [insert name] |  |  | Event Materials List
| Print event badges | [insert name] |  | Files will be available on www.hbanet.org profile for printing | How to Create Event Badges
Day of Event |  | [event date]
Logistics
| Arrive early for setup | [insert name]
| Display indoor/outdoor signageif needed | Onsite Volunteers
| Setup and staff registration table | Onsite Volunteers |  |  | Registraion Onsite Responsibilities
| Set up collateral table set up and materials distribution | Onsite Volunteers |  |  | Engagement Onsite Responsibilities
| Manage volunteer staff throughout event | [insert name]
| Take photos, tweet and distribute & manage networking activity | [insert name] |  |  | Marketing Onsite Responsibilities
| Manage event flow, presentation start time, etc | [insert name]
| Watch for and welcome sponsor and HBA hosts | [insert name]
Event close:
| Close down and pack up HBA table/materials | Onsite Volunteers
| Collect all signage and pack for storage | Onsite Volunteers
Post-event
Administration |  | #VALUE!
| Personal thank you note to sponsor/venue contacts | [insert name]
| Complete Event Reconciliation packet and send to HBA Central | [insert name] |  |  | Post-Event Reconciliation Instructions
| Summarize feedback surveys | Market Research
| Ensure completion of HBA In-Kind form by sponsor | [insert name] |  | Send complete In-Kind form to HBA Finance Department as indicated on form
Marketing |  | #VALUE!
| Review and select photos for marketing efforts/post event materials | [insert name]
| Archive event photos, etc | [insert name]
Programs |  | #VALUE!
| Conduct debriefing/lessons learned with full team | [insert name] |  | What was done well? What could have been done better for next time? What feedback was given at the event? Any highlights? Focus on both the event itself as well as the full event planning process
| Share any important learnings with Regional Programming COE | [insert name] |  | They will incorporate into regional best practices and learnings