## Unsponsored Networking Event
HBA Event Planning Checklist
This checklist will walk you step-by-step through the planning process from start to finish. Event planning is a detailed and intricate process so this checklist might look overwhelming at first. Please use the list in bite-sized pieces based upon where you are in the process to make the list more manageable for your team.
Please enter your event date (or target event date) where indicated in red, as well as event planning team members name to take advantage of the full functionality of this checklist
Event details: |  |  | Event Planning Team | Name
Event Date: | [event date] |  | Event Logistics: | [insert name]
Event Title: |  |  | Content | [insert name]
Location/sponsor: |  |  | Sponsor/venue: | [insert name]
|  |  | Marketing liaison: | [insert name]
|  |  | Membership and Volunteer liaison: | [insert name]
X | Planning Item | Due date and action owner | Status / Comments / Followups | Notes / next steps | Resources/tools
X | Set up weekly Event Planning meeting w/ full team | [insert name]
By Week 12 |  | #VALUE!
| Confirm potential event date(s) | [insert name] |  | Confer with Programming DAL to ensure date works for all parties. Please avoid holidays, other events occuring in your chapter, as well as any HBA Central events. Check the Global Planning Calendar. | Global Planning Calendar
| Determine event venue and secure the following details: | [insert name] |  | Aim for free or moderately priced venues with a professional/quiet atmosphere. Input all final details onto Event Setup Form | HBA Event Setup Form - Networking
• Address / directions to location
• Capacity of event room or space
• Reservation or room rental (if needed)
| • Any special instructions |  |  | i.e. arrival, parking or security info needed for attendees
Week 10 |  | #VALUE!
Marketing and Finance Workstream - 8-9 weeks out |  | #VALUE!
| Review and confirm the following with your chapter vice president: | [insert name] |  | VP will discuss any needs with regional treasurer and committees
• Event budget
• Event revenue targets
| • Event pricing (members only) |  |  |  | HBA Core Programming Guidance
• Payment method and/or invoicing
• Necessary discount codes
| • Any contracts that may need to be signed |  |  | Regional Treasurer is the only volunteer authorized to sign contracts and legal documents
| Marketing reviews and adds "sizzle" to event title, short description and event details, then returns to Event Logistics volunteer | [insert name]
Week 9 |  | #VALUE!
| Determine onsite volunteer staffing needs | [insert name] |  |  | Event Volunteer Staffing Grid
| Develop event marketing strategy | [insert name] |  | Determine frequecy of social media/other promotion.
| Compile all final event information onto HBA Event Setup Form | [insert name]
Week 8 |  | #VALUE!
| Submit Event Setup Form to HBA Central | [insert name] |  | Submit in your HBA profile under "Event Setup Form"
| Event registration page set up online | HBA Central |  | Once reviewed and approved, your event registration page will be published to the website.
| Event will be automatically included in weekly Event Digest emails | HBA Central
| Event feedback surveys created and set to go out immediately post-event | HBA Central
| Confirmation email will be sent to the volunteer who submitted the form w/ registration link and all discount codes | HBA Central
Week 7 |  | #VALUE!
| Create marketing materials in Marq and provide to planning team | [insert name]
| Implement marketing/advertising plan | [insert name] |  | Social media, newsletter, Board promotion, other.
| Begin monitoring event attendance | [insert name] |  | Programming DAL has access to real-time event attendance reports and should provide to team regularly to monitor attendance. If attendance is low, consider revising marketing plan. | How to access Event Attendance Reports
Week 6 |  | #VALUE!
| Venue floor plan / layout: | [insert name]
| Overall room setup |  |  | Discuss where networking area will be with collateral table, food/bev setup, etc
Expected event flow/traffic
| Registration area (tables, chairs, easels) |  |  | 1 table for registration, chairs, table cloth (if availalble), trash can, coat rack (if needed)
| Collateral area |  |  | Table near networking area for HBA membership/volunteer info, affinity group info, etc
| Food / refreshments |  |  | Snacks or offer a 'lite dinner'; offer a few vegetarian/gluten free options; Cash bars often preferred for networking events.
Week 5 |  | #VALUE!
| Review all logistics items provided venue liaison and follow up if necessary | [insert name] |  | Confirm all internal logistical planning details are sufficient for the event
Week 4 |  | #VALUE!
| Identify HBA 'host' for the event | [insert name] |  | HBA Host: chapter EC/board/committee member(s) to handle HBA welcome and/or closing remarks
| Assign all Onsite volunteer roles and disseminate discount codes for registration | [insert name]
| Complete Event Volunteer Staffing Grid | [insert name] |  | Share with event logistics volunteer
Week 3 |  | #VALUE!
| Brief Board on program objectives, venue, speaker | Programming DAL
| Prepare 'networking' activity (if applicable) | [insert name] |  | Design / decide on activity and provide the materials. Examples include 'Meet Me Bingo'; find your sticker-mate. Align game to meeting topic or theme if possible.
Week 2 |  | #VALUE!
| Confirm/finalize event materials needs | [insert name] |  | Speaker gift(s), registration needs, marketing collateral materials, etc. | Event Materials List
| Purchase name badge paper/holders | [insert name] |  | Any type can be purchased through Amazon or your local office supply store. Keep your receipt and submit for reimbursement to your regional treasurer.
| Arrange for signage (if needed) | [insert name]
Week 1 |  | #VALUE!
| Confirm estimated final headcount; alert venue / caterer and adjust reservation if needed | [insert name]
| Confirm all working volunteers and arrival times | [insert name]
| Complete all event materials preparation | [insert name] |  |  | Event Materials List
| Print event badges | [insert name] |  | Instructions on how to create a mail merge with your registration list can be found in the HBA online Resource Center. | How to Create Event Badges
Day of Event |  | [event date]
Logistics
| Arrive early for setup | [insert name]
| Display indoor/outdoor signageif needed | Onsite Volunteers
| Setup and staff registration table | Onsite Volunteers |  |  | Registraion Onsite Responsibilities
| Set up collateral table set up | Onsite Volunteers |  |  | Engagement Onsite Responsibilities
| Manage volunteer staff throughout event | [insert name]
| Take photos & manage networking activity | [insert name] |  |  | Marketing Onsite Responsibilities
Event close:
| Close down and pack up HBA table/materials | Onsite Volunteers
| Collect all signage and pack for storage | Onsite Volunteers
Post-event
Administration |  | #VALUE!
| Complete Event Reconciliation packet and send to HBA Central | [insert name] |  |  | Post-Event Reconciliation Instructions
| Summarize feedback surveys | Market Research
Marketing |  | #VALUE!
| Review and select photos for marketing efforts/post event materials | [insert name]
| Archive event photos, etc | [insert name]
Programs |  | #VALUE!
| Conduct debriefing/lessons learned with full team | [insert name] |  | What was done well? What could have been done better for next time? What feedback was given at the event? Any highlights? Focus on both the event itself as well as the full event planning process
| Share any important learnings with Regional Programming President | [insert name] |  | They will incorporate into regional best practices and learnings

## Sponsored Networking Event
HBA Event Planning Checklist
This checklist will walk you step-by-step through the planning process from start to finish. Event planning is a detailed and intricate process so this checklist might look overwhelming at first. Please use the list in bite-sized pieces based upon where you are in the process to make the list more manageable for your team.
Please enter your event date (or target event date) where indicated in red, as well as event planning team members name to take advantage of the full functionality of this checklist
Event details: |  |  | Event Planning Team | Name
Event Date: | [event date] |  | Event Logistics: | [insert name]
Event Title: |  |  | Content | [insert name]
Location/sponsor: |  |  | Sponsor/venue: | [insert name]
|  |  | Marketing liaison: | [insert name]
|  |  | Membership and Volunteer liaison: | [insert name]
X | Planning Item | Due date and action owner | Status / Comments / Followups | Notes / next steps | Resources/tools
X | Set up weekly Event Planning meeting w/ full team | [insert name]
By Week 12 |  | #VALUE!
| Confirm potential event date(s) with venue/sponsor | [insert name] |  | Confer with Programming DAL to ensure date works for all parties. Please avoid holidays, other events scheduled in your chapter, as well as HBA Central events | Global Planning Calendar
| Secure from venue/sponsor: | [insert name] |  | Input all final details onto Event Setup Form | HBA Event Setup Form - Networking
• Directions to location
• Capacity of event room
• Reservation or room rental (if needed)
| • Any special instructions |  |  | i.e. arrival, parking or security info needed for attendees
| Secure preferred company logo and website | [insert name]
| Share HBA Event Sponsorship Form with sponsor company with instruction that they complete now for cash sponsorship and soon following event for in-kind sponsorship | [insert name] |  |  | HBA Event Sponsorship Form
Week 10 |  | #VALUE!
Marketing and Finance Workstream - 8-9 weeks out |  | #VALUE!
| Review and confirm the following with your chapter vice president: | [insert name] |  | VP will discuss any needs with regional treasurer and committees
• Event budget
• Event revenue targets
| • Event pricing (members only) |  |  |  | HBA Core Programming Guidance
• Payment method and/or invoicing
• Necessary discount codes
| • Any contracts that may need to be signed |  |  | Regional Treasurer is the only volunteer authorized to sign contracts and legal documents
| Marketing reviews and adds "sizzle" to event title, short description and event details, then returns to Event Logistics volunteer | [insert name]
Week 9 |  | #VALUE!
| Determine onsite volunteer staffing needs | [insert name] |  | Refer to Onsite Team Roles tab of this workbook to assist in determining needs. | Event Volunteer Staffing Grid
| Develop event marketing strategy | [insert name] |  | Determine frequecy of social media/other promotion.
| Compile all final event information onto HBA Event Setup Form | [insert name]
Week 8 |  | #VALUE!
| Submit Event Setup Form to HBA Central | [insert name] |  | Form can be found in your HBA profile under "Event Setup Form"
| Event registration page set up online | HBA Central |  | After review and approval, the event registration page will be published to the HBA website.
| Event will be automatically included in weekly Event Digest emails | HBA Central
| Event feedback surveys created and set to go out immediately post-event | HBA Central
| Confirmation email sent to volunteer who submitted the Event Setup Form w/ registration link and all discount codes | HBA Central
Week 7 |  | #VALUE!
| Create marketing materials in Marq and provide to planning team | [insert name]
| Implement marketing plan | [insert name] |  | Social media, newsletter, Board promotion, other.
| Begin monitoring event attendance | [insert name] |  | Programming DAL has access to real-time event attendance reports and should provide to team regularly. If attendance is low, consider revising marketing plan | How to access Event Attendance Reports
Week 6 |  | #VALUE!
Venue/sponsor internal planning
| Venue floor plan / layout: | [insert name]
| Overall room setup |  |  | Discuss where networking area will be with collateral table, food/bev setup, etc
Expected event flow/traffic
| Registration area (tables, chairs, easels) |  |  | 1 table for registration, chairs, table cloth (if available), trash can, coat rack (if needed)
| Collateral area |  |  | Table near networking area for HBA membership/volunteer info, affinity group info, etc
| Food / refreshments |  |  | Snacks or "light dinner"; offer a few vegetarian/gluten free options; Cash bars often preferred for networking events.
Week 5 |  | #VALUE!
| Sponsored event: confirm Sponsor "Host" for welcome remarks | [insert name]
| Review all logistics items provided by sponsor/venue liaison and follow up if necessary | [insert name] |  | Confirm all internal logistical planning details are sufficient for the event
Week 4 |  | #VALUE!
| Identify HBA 'host' for the event | [insert name] |  | HBA Host: chapter EC/board/committee member(s) to handle HBA welcome and/or closing remarks
| Assign all Onsite volunteer roles and disseminate discount codes for registration | [insert name]
| Complete Event Volunteer Staffing Grid | [insert name] |  | Share with event logistics volunteer
Week 3 |  | #VALUE!
| Brief Board on program objectives, venue, speaker | Programming DAL
| Prepare 'networking' activity (if applicable) | [insert name] |  | Design / decide on activity and provide the materials. Examples include 'Meet Me Bingo'; find your sticker-mate. Align game to meeting topic or theme if possible.
Week 2 |  | #VALUE!
| Confirm/finalize event materials needs | [insert name] |  | Speaker gift(s), registration needs, marketing collateral materials, etc. | Event Materials List
| Purchase name badge paper/holders | Notes / next steps |  | Any type can be purchased through Amazon or your local office supply store. Keep your receipt and submit for reimbursement to your regional treasurer.
| Arrange for signage (if needed) | [insert name]
Week 1 |  | #VALUE!
| Confirm estimated final headcount; alert venue / caterer and adjust reservation if needed | [insert name]
| Confirm all working volunteers and arrival times | [insert name]
| Complete all event materials preparation | [insert name] |  |  | Event Materials List
| Print event badges | [insert name] |  | Instructions on how to do a mail merge with your registration list are available in the HBA online Resource Center. | How to Create Event Badges
Day of Event |  | [event date]
Logistics
| Arrive early for setup | [insert name]
| Display indoor/outdoor signageif needed | Onsite Volunteers
| Setup and staff registration table | Onsite Volunteers |  |  | Registraion Onsite Responsibilities
| Set up collateral table set up and materials distribution | Onsite Volunteers |  |  | Engagement Onsite Responsibilities
| Manage volunteer staff throughout event | [insert name]
| Manage networking activity | [insert name] |  |  | Marketing Onsite Responsibilities
| Manage event flow, presentation start time, take photos, etc | [insert name]
| Watch for and welcome sponsor and HBA hosts | [insert name]
Event close:
| Close down and pack up HBA table/materials | Onsite Volunteers
| Collect all signage and pack for storage | Onsite Volunteers
Post-event
Administration |  | #VALUE!
| Personal thank you note to sponsor/venue contacts | [insert name]
| Complete Event Reconciliation packet and send to HBA Central | [insert name] |  |  | Post-Event Reconciliation Instructions
| Summarize feedback surveys | Market Research
| Ensure completion of HBA In-Kind form by sponsor | [insert name] |  | Send complete In-Kind form to HBA Finance Department as indicated on form
Marketing |  | #VALUE!
| Review and select photos for marketing efforts/post event materials | [insert name]
| Archive event photos, etc | [insert name]
Programs |  | #VALUE!
| Conduct debriefing/lessons learned with full team | [insert name] |  | What was done well? What could have been done better for next time? What feedback was given at the event? Any highlights? Focus on both the event itself as well as the full event planning process
| Share any important learnings with Regional Programming President | [insert name] |  | They will incorporate into regional best practices and learnings