## Process and Responsibilities
Project Cycle Elements | Specific Steps | Actions in DevResults | Responsible Party | Accountable Party | Consulted Party | Informed Party
Proposal is submitted | Proposal process is managed outside of DevResults | None
Project is funded | Contract signed, money is exchanged | Create project in DevResults
| Project kickoff | Add narrative summary elements to DevResults
| Add staff or partners | Add new staff members or partners as DevResults users and assign permission levels
| Framework is completed and approved | Add results framework to DevResults
| Indicator list is completed and approved | Add precise indicator definitions to DevResults and assign them to the project
Project is launched | Establish data collection plan | Revise data source for indicators as necessary. Will indicators be reported per location? Per district? Will data be entered as aggregate results or via data tables?
| Establish the geographic places where the project will operate and report data | Verify GPS points, add locations to DevResults, then assign locations and administrative divisions to the project
| Create data tables | Define the data tables for collecting data; map the data tables to indicator definitions; establish collection method (desktop or mobile collection tools)
Execute Project | Add program management features | Include checklists for deliverables and milestones; assign tasks to users
Data collection | Add indicator data to DevResults | Update data tables and aggregate entry fields each reporting period
Reports | Define queries | Create saved queries for indicator results
| Create forms | Create DevResults forms for producing paperwork from DevResults
| Produce reports | Develop internal protocol for adding tables, maps, and graphs to reports
Analysis | Make evidence-based decisions | Do your indicator results suggest that changes need to be made to the operation of the project?